## Product backlog
Product Backlog
„Computational cluster”
ID	As a/an …	I want to …	NOTES	PRIORITY	STATUS
0	Any component user	Use the component with comfortable user interface.		low	DONE
1	Any component user	Use the component from command line.	Command line flags handling.	required	DONE
2	Task Manager user, Computational Node user	Register to the server / disconnect from the server anytime with no influence on result consistency.		required	TODO
3	Computational client user	Have an information about computation progress during computation performance.		low	TODO
4	Any component user	Be sure that the result will be consistent in case of any component failure.	Besides all primary and backup communication servers failure.	required	TODO
5	Communication server administrator	Be able to monitor system resources usage.		low	TODO
6	Any component user	Have an information about connection status (accepted / rejected).		low	TODO
7	Computational client user	Have no influence (and not to be influenced) to other users computation.		required	TODO
8	Computational client user	Perform computation of any implemented algorithm.		required	TODO
9	Communication server administrator	Be able to save run configuration in a configuration file.		required	TODO
10	Communication server administrator	System to stay stable in case of invalid message format.		required	TODO
11	Any component user	Communicate with other components over TCP/IP protocol.		required	TODO
12	Computational client user	Have built-in DVRP algorithm.		required	TODO
13	Communication server administrator	Messages to be compatible with specified XML Schema documents, so they can be easily understood by human.		required	TODO
14	Any component user	Exchange messages among proper components through communication server.		required	TODO

## Sprints backlogs
Sprints Backlogs
„Computational Cluster”
SPRINT	USER STORY	TASKS	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	← hours spent
1	(0) As any component user I want to use the component with comfortable user interface	Design and implement graphical user interfaces.	3
	(1) As any component user I want to use the component from command line.	Add command line flags handling to all components.					3
2	(6) As any component user I want to have information about connection status (accepted / rejected)	Implement java sockets communication over TCP/IP	2		3	3
	(11) As any component user I want to communicate with other components over TCP/IP protocol.
	(14) As any component user I want to exchange messages with proper components through communication server.	Implement communication server message passing.			3	3
3	(13) As communication server administrator I want messages to be compatible with specified XML Schema documents, so they can be easily understood by human.	Implement testing every message against proper XML Schema document.	2		3	4
	(10) As a communication server administrator I want system to stay stable in case of invalid message format.	Implement rejecting invalid messages (without error handling, invalid message can cause computation stopping)			2
4	(12) As a computational client user I want to have built-in DVRP algorithm.	Design and implement outline of the algorithm.	2		4	4
5	(12) As a computational client user I want to have built-in DVRP algorithm.	Implement a test the algorithm.	2		4	4
6	(2) As task manager / computational node user I want to register to the server / disconnect from the server anytime with no influence on result consistency.	Add error handling. In case of losing connection to computational node / task manager, system should immediatly find new component to handle the job (including just-connected components)	2		4	4
	(4) As a computational client user Be sure that the result will be consistent in case of any component failure.
	(7) As a computational client user I want to have no influence (and not to be influenced) to other users computation.	Handle errors in communication if present.			1	1
7	(4) As a computational client user Be sure that the result will be consistent in case of any component failure.	Add backup server	4		4	8
8	(8) As a computational client user I want to perform computation of any implemented algorithm.	Test the system with other (simple) algorithm compatible with the system.	4		4
9 / 10 / 11 / 12	(3) As a computational client user I want to have an information about computation progress during computation performance.	Final corrections.	3		2	2
	(5) As a communication server administrator I want to be able to monitor system resources usage.
	(9) As a communication server administrator I want to be able to save run configuration in a configuration file.