## Product backlog
Product Backlog
„Computational cluster”
ID	As a/an …	I want to …	NOTES	PRIORITY	STATUS
0	Any component user	Use the component with comfortable user interface.		low	DONE
1	Any component user	Use the component from command line.	Command line flags handling.	required	DONE
2	Task Manager user, Computational Node user	Register to the server / disconnect from the server anytime with no influence on result consistency.		required	TODO
3	Computational client user	Have an information about computation progress during computation performance.		low	TODO
4	Any component user	Be sure that the result will be consistent in case of any component failure.	Besides all primary and backup communication servers failure.	required	TODO
5	Communication server administrator	Be able to monitor system resources usage.		low	TODO
6	Any component user	Have an information about connection status (accepted / rejected).		low	TODO
7	Computational client user	Have no influence (and not to be influenced) to other users computation.		required	TODO
8	Computational client user	Perform computation of any implemented algorithm.		required	TODO
9	Communication server administrator	Be able to save run configuration in a configuration file.		required	TODO
10	Communication server administrator	System to stay stable in case of invalid message format.		required	TODO
11	Any component user	Communicate with other components over TCP/IP protocol.		required	TODO
12	Computational client user	Have built-in DVRP algorithm.		required	TODO
13	Communication server administrator	Messages to be compatible with specified XML Schema documents, so they can be easily understood by human.		required	TODO
14	Any component user	Exchange messages among proper components through communication server.		required	TODO

## Sprints backlogs
Sprints Backlogs
„Computational Cluster”
SPRINT	USER STORY	TASKS	Estimated time for Monday	Estimated time for Tuesday	Estimated time for Wednesday	Estimated time for Thursday	Estimated time for Friday	Estimated time for Saturday	Estimated time for Sunday	Actual time for Monday	Actual time for Tuesday	Actual time for Wednesday	Actual time for Thursday	Actual time for Friday	Actual time for Saturday	Actual time for Sunday	Person(s) responsible for completing task
0	As user I want to use the components with comfortable user interface.	Create generic gui interface that will provide consistent look for every cluster object.	2	0	0	0	0	0	0	2	0	0	0	0	0	0	Piotr
		Gui interface for ComputationalServer	1	1	0	0	0	0	0	1	1	0	0	0	0	0	Piotr
		Gui interface for ComputationalClient	2	2	0	0	0	0	0	2	2	0	0	0	0	0	Anna
		Gui interface for ComputationalNode	1	1	0	0	0	0	0	1	1	0	0	0	0	0	Monika
		Gui interface for TaskManager	1	1	0	0	0	0	0	1	1	0	0	0	0	0	Filip
	As user I want to be able to run components with no gui (in terminal) and be able to override default settings by providing flags.	Make components run without gui	1	1	0	0	0	0	0	1	0	0	0	0	0	0	All
		Read and parse flags provided within terminal command	1	1	1	0	0	0	0	1	1	0	0	0	0	0	Filip
		React to flags (override default settings)	1	1	1	0	0	0	0	1	1	0	0	0	0	0	Piotr
		Make components run with default settings when no flags are specified	1	1	1	0	0	0	0	1	1	0	0	0	0	0	Piotr
1	As user I want to be able to connect to server (and get error message if it didn'w work).	Add 'Connect' button behaviour consistent across all components and disable this button if provided data for connection is not valid (e.g. bad IP address)	0	0	1	0	0	0	0	0	0	1	0	0	0	0	Piotr
		Add generic method providing routine for every component to connect to server	0	0	1	0	0	0	0	0	0	1	0	0	0	0	Filip
		Add actual message sending through Java sockets	0	0	1	0	0	0	0	0	0	1	0	0	0	0	Filip, Piotr
	As user I want to be informed about connection status	Add ComputationalServer fields behaviour that will display connected components	0	0	0	0	0	2	0	0	0	0	0	1			Piotr
		Implement message queue in ComputationalServer class	0	0	1	0	0	0	0	0	0	1	0	0			Piotr
		Implement message handling by server (create special threads that will receive it and respond to it)	0	0	1	0	0	0	0	0	0	1	0	0			Piotr
		Implement generic message interface that will be used by every message	0	0	1	0	0	0	0	0	0	1	0	0			Monika
		Implement error reporting when connection goes wrong	0	0	1	0	0	0	0	0	0	1	0	0			Anna
		Monitor connection status routine for GenericComponent	0	0	0	0	0	1	0	0	0	0	0	0			Piotr
		Resend message within provided timeout (method for GenericComponent)	0	0	0	0	0	1	0	0	0	0	0	1			Piotr
		Refactor code	0	0	1	0	0	0	0	0	0	2	0	0			Piotr